Timeline for Smart Policing: Operation LASER+

Los Angeles Police Department

October 1, 2016 to December 31. 2017

October 1 to December 31, 2016 – LASER+ will add four more LAPD patrol divisions:  Olympic and Hollywood (West Bureau), and Foothill and Mission (Valley Bureau). This means that LASER will be active in 12 patrol divisions and in Air Support, Metro, and Community Relationships divisions (15 in total).

The BJA Training and Technical Assistance provider, CNA will provide training on ArcGIS, social network analysis and other topics for members of the LASER+ teams.

January to March 2017.  Training and technical assistance will be provided to the four new Divisions and refresher courses will be provided to the existing Divisions.

February 2017 – Presentation of LASER+ at the LAPD Crime Fighter's Conference

April – December 2017 – All LASER+ Bureaus, Divisions, CIDs, and the LAPD Research Partner (Justice & Security Strategies/JSS) will engage in the following activities:

- Identify specific hot spot corridors (LASER Zones) in 12 divisions

- Intervene in LASER Zones using patrol, special units, Metro, and Air Support

- Create chronic offender bulletins that follow the appropriate protocols

- Monitor and track chronic offenders

- Use social network analysis to determine the linkages between and among gangs and gang members across Division and Bureau boundaries

- Use call-in meetings (focused deterrence) to deter shootings and violence at the Division and Bureau levels

- Measure enforcement activities weekly

- Provide 4-week reports to Deputy Chiefs, Commanders, and Captains

Quarterly reports – December 31, 2016 and March 31, June 30, September 30, and December 31, 2017 – provide quarterly reports to LAPD command staff and BJA regarding the progress of LASER+

Semi-Annual reports –December 2016, June 2017 and December 2017.  These reports will be filed through the Grants Management System

September 2017 – JSS will provide the LAPD and BJA with an evaluation report on LASER+

December 31, 2017 – Grant ends; final report submitted January 2018.